## Slide 1: PROJECT PLAN
Team X Review

## Slide 2: Proposal
The members of Team X propose to develop a therapeutic activity system using a Microsoft Surface unit and a Windows 7 desktop. By working in conjunction with critical experts at Texas Health Resources (THR), Team X will create a system which will allow physical therapy patients to participate in a variety of activities, participating clinicians to customize the therapy and neurologists to analyze the data collected during participation in each activity. The intent of the system is to have patient activities take place on the Microsoft Surface with clinician administration activities and data analysis/viewing to be done through a Windows 7 desktop application. Team X will be utilizing the existing framework and database structure from the Healing Touch software and Healing Vision application developed by the Senior Design class at TCU in 2010-2011.

## Slide 3: Roles and Responsibilities
Scott Boykin – Surface programming lead, Joint technical lead, Design
Adam Burt – Website lead, Surface programing, Design, Graphics
Cristina Cline – Project Manager, Collaborative lead, Desktop application lead
Jeffrey Gettel – Database lead, Testing Lead
Andrew Hughes – Testing
Joey Wilkinson – Scheduling lead, Graphics, Database

## Slide 4: Schedule
Milestones | Date
Project Support Environment | 09/27/2011
Project Proposal | 09/27/2011
Project Plan Documentation V1.0 | 10/06/2011
Requirements Documentation V1.0 | 10/20/2011
Design Documentation V1.0 | 11/08/2011
Test Plan Documentation V1.0 | 11/29/2011
Iteration # 1 | 12/13/2011
NTASC Submission | 03/13/2012
NTASC Conference | 03/31/2012
SRS Poster Deadline | 04/06/2012
Student Research Symposium | 04/15/2012
Final Presentation | 04/29/2012

## Slide 5: Risk Analysis
ID | RISK | PROBABILITY | EFFECTS
1 | Hardware/system failure in the Surface unit | Low | Catastrophic
2 | Requirements change without notice to the extent of a major refactor | Low | Serious
3 | Team members sick or absent at critical moments | Moderate | Serious
4 | Requirements change, causing minor updates | High | Tolerable
5 | Underestimation of code completion time | Low/Moderate | Tolerable
6 | Consistent missing of deadlines by team members | Low | Tolerable
7 | Server failure causing data loss | Low | Tolerable

## Slide 6: Risk Management Strategy
ID | STRATEGY
1 | Contact Microsoft to consult on resolution strategy. Testing can be done on PC using simulator. If necessary, can borrow resources from Team Y until issue resolved
2 | Inform client of effects such a drastic change. Design framework to more easily accommodate changes and identify solutions. Immediately meet as a team to collectively develop a plan of action.
3 | Each team member has been assigned a backup responsible for keeping up with the task to easily take over if necessary. Team members are tasked with documenting progress and activities.
4 | Design framework to more easily accommodate changes. Immediately address changes as a group and inform client of any changes to schedule.
5 | Re-evaluate estimation techniques and adjust for next iteration. If necessary, increase modularity of coding tasks to streamline efforts.
6 | Maintain weekly status reports. Re-allocate tasks as necessary.
7 | Maintain working models of DB structure, including tables, stored procedures and queries to easily recreate DB if necessary. Data can be re-entered.

## Slide 7: Meetings and Communication
During Iteration #1, Team X meets every Friday at 1430 in the Senior Design Lab (Room 330 of the Tucker Technology Center at TCU). During these meetings, we discuss the weekly status of each member and address any issues that have come up during the previous week. We also discuss the plans and assigned tasks for each member during the following week. Team X also meets every Tuesday and Thursday at 1100, which is the regularly scheduled class time.
The primary method of communication for Team X is e-mail. Each team member has provided at least one working, current email address. Each email address has been added to one Google team to create a distribution list for more efficient communication between team members. Team X created a Google Site to post messages, notes, documents, questions, etc. This is intended to serve as a means to maintain communication and collaboration outside of meeting and class times. Members of Team X have all provided each other with working phone numbers as well. Each team member is responsible for contacting the project manager in the event of an impending absence or late arrival.

## Slide 8: Monitoring and Reporting
Each major task involved in this project has been assigned to a team member as the lead and each lead has been assigned a backup team member. This backup team member is responsible for maintaining a working knowledge of the activities and progress of the lead for that task. This structure not only supplements the risk management strategy but serves as a system of checks and balances. Each team member is responsible for their own individual tasks and schedule as well as those of other individuals working on the same aspects of the project. At certain points throughout the duration of the project (i.e. – completion of code for certain functionality, documentation completion, design decision/changes, etc.) the group will collectively review and analyze the project status for quality and completeness.

## Slide 9: Monitoring and Reporting (cont.)
Each task is to be completed on time, based on the schedule included in this document, and in accordance with the requirements found in the requirements documentation. The weekly status reports will be used to gauge progress and estimation completion times. While it is the responsibility of the individual team member to ensure they are on task and report any delays or deviations to the group, the project manager will monitor the progress of each team member and will reassign tasks as necessary should it become clear that any team member is unable to complete tasks on schedule.

## Slide 10: Monitoring and Reporting (cont.)
All group members are responsible for being aware of the requirements specific to their task, in addition to the requirements covered under the general scope of the project. Changes to the requirements will be discussed immediately and the appropriate course of action will be determined among everyone in the group. For the common project components (surface framework, DB structure, etc.) each team representative must collaborate with their specific team as well as the representative from the other team. Any updates, enhancements or revisions must first be reviewed by all team members before being implemented.